## Slide 1
WEEKLY PROGRESS UPDATE
iStudentPlus Website Development
Elementor → Next.js + TypeScript, with SEO & GEO optimization
7–11 Juli 2026

## Slide 2
AGENDA
What we'll cover today
1
Progress this week
What was built and shipped
2
Key corrections vs. old site
Fixes based on the client brief
3
Plan for next week
Day-by-day breakdown
4
Decisions needed from you
What's blocking further progress
02

## Slide 3
THIS WEEK
This week at a glance
14
PAGES LIVE
9
NAV SECTIONS
6
COUNTRIES COVERED
0
BUILD ERRORS
Foundation shipped this week
Next.js 16 + TypeScript + Tailwind, rebuilt to match the official site-structure brief — light theme in the real iStudentPlus brand colors (navy + pink), production build passing with zero errors.
03

## Slide 4
SITE STRUCTURE
Every section now matches the client brief
1
Home
Hero, 6-step journey, consultation form
2
About Us
Mission, offices, our team
3
Study Abroad
Australia, UK, USA, Canada, China, Japan
4
Services
Visa & Admission, Admission Counselling
5
Courses & Universities
VET/Diploma → PhD, qualification filter
6
Language Programs
General English, Conversation, IELTS, JLPT
7
Blog
Recent News, Immigration, Student Life, Study Tips
8
Contact Us
Offices, WhatsApp, social media
04

## Slide 5
KEY CORRECTIONS
What changed after the client brief arrived
AREA
BEFORE
AFTER (THIS WEEK)
Office locations
Sydney, Australia (from old site scrape)
Pangkalpinang & Makassar, Indonesia — Jakarta coming soon
Team page
No real names or bios
Cindy Christella (CEO) & Nur Fadillah, with real bio
Navigation
5 simple links
8 sections with dropdown submenus, matching the brief exactly
Main CTA
WhatsApp button only
“Book Free Consultation” + full embedded form on Home
05

## Slide 6
HONEST SCOPE
What we deliberately did not build yet
!
Language Course Enrollment (registration → payment → calendar → reminder)
This needs a payment gateway and a booking/calendar system — real backend work, not just page design. We paused here on purpose so the site structure and content could be finished and confirmed first.
Tracked as its own backlog item — see “Decisions Needed” for what unlocks it.
Why we work this way
Ship structure and content first — it's what you review and correct fastest.
Payment/booking flows are expensive to redo — build once, after scope is confirmed.
Every deferred item is written down here, not silently dropped.
06

## Slide 7
NEXT WEEK
Four workstreams for next week
1
SEO & GEO Foundation
sitemap.xml, robots.txt, llms.txt, structured data pass
2
Content Finalization
Confirm office contact info, get team photos & bios
3
QA & Performance
Mobile/tablet pass, accessibility, Lighthouse check
4
Staging & Review
Deploy to staging, walk through with the team
07

## Slide 8
NEXT WEEK — BREAKDOWN
Day-by-day plan, 14–18 Juli 2026
Day | Focus | Key tasks
Sen 14 Jul | SEO & GEO Foundation | sitemap.xml, robots.txt, llms.txt, per-page metadata polish, verify structured data
Sel 15 Jul | Content Finalization | Confirm valid office phone/email, collect Cindy's photo & bio, real partner logos
Rab 16 Jul | QA — Responsive | Mobile/tablet pass across all 14 pages, fix layout issues found
Kam 17 Jul | QA — Performance & A11y | Lighthouse pass, image optimization, keyboard nav & contrast check
Jum 18 Jul | Staging & Review | Deploy to staging, walkthrough with team, log feedback as next backlog
08

## Slide 9
WE NEED YOUR INPUT
Four decisions that unlock next steps
?
Cindy Christella's bio & photo
Team page currently shows an honest placeholder — needs 1–2 paragraphs + photo (also a photo for Nur Fadillah).
?
Valid contact details
Old site's phone/address were leftover theme demo data — please confirm the real office phone, email, and address.
?
CMS vs. static content
Should Blog/content be editable via a CMS, or is code-managed content fine for now?
?
Enrollment & payment priority
When should Language Course Enrollment (payment + calendar) start — and which payment gateway do you use?
09

## Slide 10
Thank you
Questions, feedback, or the four decisions above — happy to go through any of it now.
iStudentPlus Website Development · Weekly Progress Update